## Calendar View
Month |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April
Day |  | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
Date |  | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28
[26 empty] | Du | Du | Si | Si | Sy | Sy | Lo | Lo | NY | NY | SP | SP | Easter | MC | MC
Dubai | bar: Du; Lo; SP
Key Dates | bar: Du; Lo; SP
| Dates to avoid (Public/National Holidays, etc) | [5 empty] | 15 | [10 empty] | 1 | 2/3/4 |  |  |  | 1 |  |  | NY: 29/30; SP: 31/1
Indicative show dates | bar: Du to Du
Debriefs / wrap up | bar: Sy
Venues
| Venue search starts |  | X | X | X | X | X | X
| Client interest gathered |  |  |  |  | X | X | X | X
| Indicative site visit | [7 empty] | X | X | X
| Client approval Step 1 | [10 empty] | X | X
| Payment plan established | [10 empty] | X | X
| Contract & payment plans reviewed | [11 empty] | X | X
| Contracts signed | [12 empty] | X | X | X
Design & Operations (incl lounges)
| Design discussions | [6 empty] | X | X | X | X | X | X | X
| Finalize designs | [11 empty] | X | X
| Appoint suppliers | [11 empty] | X | X | X
| Contract design elements | [13 empty] | X | X
| Contract AV suppliers & 3rd Parties | [13 empty] | X | X | X
Staffing & Staff Infrastructure
| Staffing shared & finalised | [11 empty] | X | X
| Book accommodation and flights | [14 empty] | X | X
Keynote & Content
| Contact and prep speakers | [16 empty] | X | X | X | X | X
| Establish Run of Show | [15 empty] | X | X | X | X
| Room plans drafted | [16 empty] | X | X | X
| Room plans submitted | [18 empty] | X | X | X
| Assets & content collated | [18 empty] | X | X |  |  | X | X
Registration, Housing & Staffing
| Registration set up | [15 empty] | X | X | X | X
| Housing Confirmed | [17 empty] | X | X | X
| Ambassadors & Reg staff sourced | [18 empty] | X | X | X
Singapore
Key Dates
| Dates to avoid (Public/National Holidays, etc) | 9 | [11 empty] | 31 | [7 empty] | 25 | 1 |  |  | Du: 29/30; SP: 31 | 18 |  | 1
Indicative show dates | bar: Si to Si
Debriefs / wrap up | bar: Lo
Venues
| Venue search starts |  |  |  | X | X | X | X | X | X
| Client interest gathered | [6 empty] | X | X | X | X
| Indicative site visit | [9 empty] | X | X | X
| Client approval Step 1 | [12 empty] | X | X
| Payment plan established | [12 empty] | X | X
| Contract & payment plans reviewed | [13 empty] | X | X
| Contracts signed | [14 empty] | X | X | X
Design & Operations (incl lounges)
| Design discussions | [8 empty] | X | X | X | X | X | X | X
| Finalize designs | [13 empty] | X | X
| Appoint suppliers | [13 empty] | X | X | X
| Contract design elements | [15 empty] | X | X
| Contract AV suppliers & 3rd Parties | [15 empty] | X | X | X
Staffing & Staff Infrastructure
| Staffing shared & finalised | [13 empty] | X | X
| Book accommodation and flights | [16 empty] | X | X
Keynote & Content
| Contact and prep speakers | [18 empty] | X | X |  | X | X | X
| Establish Run of Show | [17 empty] | X | X | X |  | X
| Room plans drafted | [18 empty] | X | X |  | X
| Room plans submitted | [21 empty] | X | X | X
| Assets & content collated | [21 empty] | X | X | X | bar: Du
Registration, Housing & Staffing
| Registration set up | [17 empty] | X | X | X |  | X
| Housing Confirmed | [19 empty] | X |  | X | X
| Ambassadors & Reg staff sourced and booked | [21 empty] | X | X | X
Sydney
Key Dates
| Dates to avoid (Public/National Holidays, etc) | [9 empty] | 7 | [10 empty] | 25 | 1 |  |  | Du: 27 | 18-20 | 21/25
Indicative show dates | bar: Sy to Sy
Debriefs / wrap up | bar: NY
Venues
| Venue search starts | [5 empty] | X | X | X | X | X | X
| Client interest gathered | [8 empty] | X | X | X | X
| Indicative site visit | [11 empty] | X | X | X
| Client approval Step 1 | [14 empty] | X | X
| Payment plan established | [14 empty] | X | X
| Contract & payment plans reviewed | [15 empty] | X | X
| Contracts signed | [16 empty] | X | X | X
Design & Operations (incl lounges)
| Design discussions | [10 empty] | X | X | X | X | X | X | X
| Finalize designs | [15 empty] | X | X
| Appoint suppliers | [15 empty] | X | X | X
| Contract design elements | [17 empty] | X | X
| Contract AV suppliers & 3rd Parties | [17 empty] | X | X | X
Staffing & Staff Infrastructure
| Staffing shared & finalised | [15 empty] | X | X
| Book accommodation and flights | [18 empty] | X | X
Keynote & Content
| Contact and prep speakers | [21 empty] | X | X | X | bar: Du to Du
| Establish Run of Show | [19 empty] | X |  | X | X | X
| Room plans drafted | [21 empty] | X | X | X
| Room plans submitted | [23 empty] | X | bar: Du to Du
| Assets & content collated | [23 empty] | X | bar: Du; Si to Sy
Registration, Housing & Staffing
| Registration set up | [19 empty] | X |  | X | X | X
| Housing Confirmed | [22 empty] | X | X | bar: Du
| Ambassadors & Reg staff sourced and booked | [23 empty] | X | bar: Du to Du
London
Key Dates
| Dates to avoid (Public/National Holidays, etc) |  |  |  | 26 | [8 empty] | SCH | [7 empty] | 23 - 3 |  |  |  | Sy: SCH; Lo: 10+11+12; NY: 24+26; SP: SCH
Indicative show dates | bar: Lo to Lo; NY
| Debriefs / wrap up | [36 empty] | X
Venues
| Venue search starts | [6 empty] | X | X | X | X | X | X | X
| Client interest gathered | [10 empty] | X | X | X | X
| Indicative site visit | [13 empty] | X | X | X
| Client approval Step 1 | [16 empty] | X | X
| Payment plan established | [16 empty] | X | X
| Contract & payment plans reviewed | [17 empty] | X | X
| Contracts signed | [18 empty] | X | X | X
Design & Operations (incl lounges)
| Design discussions | [12 empty] | X | X | X | X | X | X | X
| Finalize designs | [17 empty] | X | X
| Appoint suppliers | [17 empty] | X | X | X
| Contract design elements | [19 empty] | X |  | X
| Contract AV suppliers & 3rd Parties | [19 empty] | X |  | X | X
Staffing & Staff Infrastructure
| Staffing shared & finalised | [17 empty] | X | X
| Book accommodation and flights | [19 empty] | X |  | X
Keynote & Content
| Contact and prep speakers | [22 empty] | X | X | bar: Du to Si
| Establish Run of Show | [21 empty] | X | X | X | bar: Du
| Room plans drafted | [22 empty] | X | X | bar: Du
Room plans submitted | bar: Du to Si
Assets & content collated | bar: Du to Du; Sy to Sy
Registration, Housing & Staffing
| Registration set up | [21 empty] | X | X | X | bar: Du
| Housing Confirmed | [23 empty] | X | bar: Du to Du
Ambassadors & Reg staff sourced and booked | bar: Du to Si
New York City | [9 empty] | 24
Key Dates
| Dates to avoid (Public/National Holidays, etc) |  |  |  |  | 2 | [5 empty] | 14 |  |  |  | 11 |  | 28 |  |  |  | 25 | 1 |  |  | Du: 20
Indicative show dates | bar: NY to NY
| Debriefs / wrap up | [36 empty] | X
Venues
| Venue search starts | [7 empty] | X | X | X | X | X | X | X | X
| Client interest gathered | [12 empty] | X | X | X | X
| Indicative site visit | [15 empty] | X | X | X
| Client approval Step 1 | [18 empty] | X | X
| Payment plan established | [18 empty] | X | X
| Contract & payment plans reviewed | [19 empty] | X |  | X
| Contracts signed | [21 empty] | X | X | X
Design & Operations (incl lounges)
| Design discussions | [14 empty] | X | X | X | X | X | X |  | X
| Finalize designs | [19 empty] | X |  | X
| Appoint suppliers | [19 empty] | X |  | X | X
| Contract design elements | [22 empty] | X | X
| Contract AV suppliers & 3rd Parties | [22 empty] | X | X | bar: Du
Staffing & Staff Infrastructure
| Staffing shared & finalised | [19 empty] | X |  | X
| Book accommodation and flights | [22 empty] | X | X
Keynote & Content
Contact and prep speakers | bar: Du to Sy
| Establish Run of Show | [23 empty] | X | bar: Du to Si
Room plans drafted | bar: Du to Si
Room plans submitted | bar: Si to Sy
Assets & content collated | bar: Si to Si; Lo to Lo
Registration, Housing & Staffing
| Registration set up | [23 empty] | X | bar: Du to Si
Housing Confirmed | bar: Du to Si
Ambassadors & Reg staff sourced and booked | bar: Si to Sy
Brazil - Sao Paulo
Key Dates
| Dates to avoid (Public/National Holidays, etc) |  |  |  |  | 7 |  |  |  |  | 12 |  |  | 2 |  | 15 | 20 |  |  |  |  | 25 | 1 | [14 empty] | 18 |  | 1
Indicative show dates | bar: SP to SP
| Debriefs / wrap up | [38 empty] | X
Venues
| Venue search starts | [11 empty] | X | X | X | X | X | X
| Client interest gathered | [14 empty] | X | X | X | X
| Indicative site visit | [17 empty] | X | X | X
| Client approval Step 1 | [21 empty] | X | X
| Payment plan established | [21 empty] | X | X
| Contract & payment plans reviewed | [22 empty] | X | X
| Contracts signed | [23 empty] | X | bar: Du to Du
Design & Operations (incl lounges)
| Design discussions | [16 empty] | X | X | X | X |  | X | X | X
| Finalize designs | [22 empty] | X | X
| Appoint suppliers | [22 empty] | X | X | bar: Du
Contract design elements | bar: Du to Du
Contract AV suppliers & 3rd Parties | bar: Du to Si
Staffing & Staff Infrastructure
| Staffing shared & finalised | [22 empty] | X | X
Book accommodation and flights | bar: Du to Si
Keynote & Content
Contact and prep speakers | bar: Si to Lo
Establish Run of Show | bar: Si to Sy
Room plans drafted | bar: Si to Sy
Room plans submitted | bar: Sy to Lo
Assets & content collated | bar: Sy to Lo; NY to NY
Registration, Housing & Staffing
Registration set up | bar: Si to Sy
Housing Confirmed | bar: Sy to Lo
Ambassadors & Reg staff sourced and booked | bar: Sy to Lo
Mexico City
Key Dates
| Dates to avoid (Public/National Holidays, etc) | [6 empty] | 16 |  | 1 | 12 |  |  | 2 |  |  | 18 |  |  | 12 |  | 25 | 1 |  |  | Si: 3; NY: 17 | 17/18 |  | 1
| Indicative show dates | [37 empty] | X | X
Debriefs / wrap up
Venues
| Venue search starts | [14 empty] | X | X | X | X | X | X
| Client interest gathered | [16 empty] | X | X | X | X
| Indicative site visit | [19 empty] | X |  | X | X
| Client approval Step 1 | [23 empty] | X | bar: Du
| Payment plan established | [23 empty] | X | bar: Du
Contract & payment plans reviewed | bar: Du to Du
Contracts signed | bar: Du to Si
Design & Operations (incl lounges)
| Design discussions | [18 empty] | X | X |  | X | X | X | bar: Du to Du
Finalize designs | bar: Du to Du
Appoint suppliers | bar: Du to Si
Contract design elements | bar: Si to Si
Contract AV suppliers & 3rd Parties | bar: Si to Sy
Staffing & Staff Infrastructure
Staffing shared & finalised | bar: Du to Du
Book accommodation and flights | bar: Si to Sy
Keynote & Content
Contact and prep speakers | bar: Sy to NY
Establish Run of Show | bar: Sy to Lo
Room plans drafted | bar: Lo to NY
Room plans submitted | bar: NY to SP
| Assets & content collated | [36 empty] | X | bar: NY to SP
Registration, Housing & Staffing
Registration set up | bar: Lo to NY
Housing Confirmed | bar: NY to SP
Ambassadors & Reg staff sourced and booked | bar: NY to SP